## Report - Individual
Week | 2
Cycle | 1
|  |  |  | Task3 | [5 empty] | Total Hours
Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Week | Cycle | Project
Dillon, Hugh | -- | -- | -- | -- | -- | -- | -- | -- | 0 | 22 | 22
Hawkins, Zac | -- | -- | -- | -- | -- | -- | -- | -- | 0 | 15 | 15
Holloway, Rick | -- | -- | 1 | -- | -- | -- | -- | -- | 1 | 21 | 21
Smith, Ben | -- | -- | -- | -- | -- | 2 | -- | -- | 2 | 17 | 17
Thorington, Hunter | -- | -- | -- | -- | -- | -- | -- | -- | 0 | 18 | 18
TOTALS | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 93 | 93
Weekly Hours | [9 empty] | Cycle 1 | Cycle 2
Dillon, Hugh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 | 0
Hawkins, Zac | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15 | 0
Holloway, Rick | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 21 | 0
Smith, Ben | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 17 | 0
Thorington, Hunter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 0

## Report - Group
Instructions: All values are automatically generated EXCEPT percentage, which must be entered manually
|  |  | Planned |  |  | Actual
Task # | Task Description (Add rows as needed) | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status (% complete) | Actual hours this cycle | Total hours
1 | Team management2 | 2 | 60 | 30 | 8.33% | 5 | 5
2 | IR land control method | 1 | 120 | 120 | 20% | 50 | 50
3 | IR camera implementation | 1 | 40 | 40 | 40% | 17 | 17
4 | Ground Station control method | 1 | 40 | 40 | 30% | 13 | 13
5 | Landing station | 2 | 20 | 10 | 2% | 1 | 1
6 | Reports | 2 | 180 | 80 | 3% | 7 | 7
7 | Marketing display | 2 | 40 | 0 | 0% | 0 | 0
8 | Integration of components | 1 | 100 | 100 | 0% | 0 | 0
|  | Planned Total1 | 600 | 420 | Actual Total | 93 | 93

## Dillon, Hugh
Name: | Dillon, Hugh
Date | Week | Task | Hours
| 1 | Team management | 5
| 1 | IR land control method | 3
| 1 | Ground Station control method | 12
| 1 | Reports | 2

## Hawkins, Zac
Name: | Hawkins, Zac
Date | Week | Task | Hours
| 1 | IR land control method | 14
| 1 | Ground Station control method | 1

## Holloway, Rick
Name: | Holloway, Rick
Date | Week | Task | Hours
| 1 | IR land control method | 17
| 1 | Landing station | 1
| 1 | Reports | 2
2014-01-31 | 2 | IR camera implementation | 1

## Smith, Ben
Name: | Smith, Ben
Date | Week | Task | Hours
| 1 | IR land control method | 14
| 1 | Reports | 1
2014-01-31 | 2 | Reports | 2

## Thorington, Hunter
Name: | Thorington, Hunter
Date | Week | Task | Hours
| 1 | IR land control method | 2
| 1 | IR camera implementation | 16

## Semester Plan
|  | Weekly Totals |  |  |  |  | Cycle 1 Totals |  |  |  |  | Cycle 2 Totals
| Task Description | Hugh | Zac | Rick | Ben | Hunter | Hugh | Zac | Rick | Ben | Hunter | Hugh | Zac | Rick | Ben | Hunter
1 | Team management | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | IR land control method | 0 | 0 | 0 | 0 | 0 | 3 | 14 | 17 | 14 | 2 | 0 | 0 | 0 | 0 | 0
3 | IR camera implementation | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 16 | 0 | 0 | 0 | 0 | 0
4 | Ground Station control method | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Landing station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Reports | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
7 | Marketing display | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Integration of components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0